## Global communication
Communication plan - global changes
Changement concerned | Priority | Purposes | Target | Medium | Tone | Kind of informations
1 - All changes, Internal communication | 1 | Make sure all managers and communications team understand why we need to do some changes | All managers and communication team | meeting | Conversational but professional | • What the change entails • What the goals of the change are • If and how their roles and teams may be impacted • What the timeframe is for the change • Where to go to get help
| 2 | Invitation to a big presentation event | All employees | mail, intranet, synchronysed agenda | Conversational | Invitation information, summary of activities
| 3 | Communicate transparently about incoming changes, and explained why it's good for the enterprise. Present for each team the 2 referrets for this project (permanent support). Introduce the intranet forum fonctionality and chats groups in order to have answers | All employees | Big event presentation, with speech, video of presentation, question/answers time, and party to celebrate the begining of a new challenge en encourage people to fully support it. | Enthousistic, | • What the change entails • What the goals of the change are • If and how their roles and teams may be impacted • What the timeframe is for the change • Where to go to get help
| 4 | Give access to all information about changes | All employees | Intranet homepage, weekly news letter | Professional | • What the change entails • What the goals of the change are • If and how their roles and teams may be impacted • What the timeframe is for the change • Where to go to get help
| 5 | Harmonize speeches and prepare answers to difficult questions. The communications team is the central pillar on which managers can rely. | All managers and communication team | meeting | Conversational but professional | prepare communicators for sensitive issues
| 6 | Calm frustrations and fears | All employees <=> managers, communication team | Intranet forum and chats | Professional | Answer all questions, use the answers prepared during the meeting with the communication team
| 7 | Communicate about training opportunities | All employees | Mail, intranet homepage, chats | Professional | What kind of training are available, why learn this, how can you progress on your post
| 8 | Give access to all training materials and documentations, all centralized in one location | All employees | Mail, intranet homepage, chats, forum | Professional | Tutorial, documentations, feedback
| 9 | Celebrate all small success and achievement | All teams | intranet publish employees interview, weekly news letter | Conversational | feedback, how he managed the changes?
| 10 | Celebrate success and achievement, team building | All employees | Meeting, conferences, big event | Conversational, profesionnal | Explain the progress made, congratulate all the teams
| 11 | Celebrate success and achievement, team building | All employees | Intranet publish photos and comments | Conversational | Show to all employees how the event 10 was fun
2 - All changes, External communication | 1 | Harmonize speeches and prepare answers to difficult questions. The communications team is the central pillar on which town hall can rely. | Internal communication team, town hall communication team, elected people ( member of the municipal council concerned) | Meeting, conferences | Professional | • What the change entails • What the goals of the change are • What the timeframe is for the change • Where to go to get help
| 2 | Propagate the information about the changes in the garbadges collection sytem | All citizens of Gotham | Publish on the town hall website, social medias | Profesionnal | • What the change entails • What the goals of the change are • What the timeframe is for the change • Where to go to get help
| 3 | Explain to the local media, the purpose of the changes, and what's the final goals of these changes | All citizens of Gotham | Press release | Profesionnal | Explain what's going on, why we 'll change waste collection system, where can citizen can found informations about it, and where they can ask their questions (town hall website)
| 4 | Propagate information about the changes on the waste collection system | All citizens of Gotham | articles publish on the municipal magazine | Professionnal | Explain what's going on, why we 'll change waste collection system, where can citizen can found informations about it, and where they can ask their questions (town hall website)
| 5 | Ensure that citizens understand that these changes will change their lives, whitout changing their tax rates | All citizens of Gotham | Advertising boards, at the underground stations, bus stops, street | Funny, professionnal, enthousiasti, | How we payed this big digital transformation (Wayn enterprise)

## Communication plan specific
Communication plan - on specific changes
Changement concerned |  | Phase | Purposes | Targets | Medium | Tone | Kind of informations
1 - use of the time manager application | Intern | 1 | After the general big presenation on next changes, present this specific change | All employees | Intranet | Professional | explain the holding and the ending of this precise change, be transparent, give all information you can
|  |  | Communication about new tasks, use productivity and collaborative tools to track tasks and help people to maintain their productivity | HR department, It department, employees | Mail, intranet support, meeting | Professional | Why and how we use the time manager application, a new workflow
|  | 2 | Individuals support | employees <=> managers/ referrents | Intranet forum, discussion chats | Conversational | Answer questions, use prepared answed, prepared during global meeting with the communication team
|  | 3 | Increase the skills of all employees | HR department, It department, employees | Meeting, Training ritual, Every day, an employee takes 15 to 20 minutes to explain to the other a specific use case | Conversational | Training, learn practices use cases
|  | 4 | Celebrate all success | HR department, It department, employees | Intranet, social networks | Conversational | Congratulate employees, show the progress made to the whole company
| Extern | 1, 2, 3 | Public announcement of the avancement of the implementation | Town Hall membership, Citizen | Social network | Promotional Professional enthousiastic | Explain the advanced
|  | 4 | Celebrate success | Town Hall membership, Citizen | Social network | Promotional Professional enthousisastic | Show the progress made
2 - Trucks with GPS | Intern | 1 | After the general big presenation on next changes, present this specific change | trucks driver, IT department, maintenance department | Intranet, meeting | Professional | explain the holding and the ending of this precise change, be transparent, give all information you can
|  |  | Communication about new tasks, use productivity and collaborative tools to track tasks and help people to maintain their productivity | trucks driver, IT department, maintenance department, team manager | Mail, intranet support, meeting | Professional | Why and how we use GPS on trucks a new workflow
|  | 2 | Individuals support | employees <=> managers/ referrents | Intranet forum, discussion chats | Conversational | Answer questions, use prepared answed, prepared during global meeting with the communication team
|  | 3 | Increase the skills of all employees | trucks driver, IT department, maintenance department, manager | Meeting, Training ritual, Every day, an employee takes 15 to 20 minutes to explain to the other a specific use case | Conversational | Training, learn practices use cases
|  | 4 | Celebrate all success | trucks driver, IT department, maintenance department | Intranet, social networks | Conversational | Congratulate employees, show the progress made to the whole company
| Extern | 1, 2, 3 | Public announcement of the avancement of the implementation | Town Hall membership, Citizen | Social network | Promotional Professional enthousiastic | Explain the advanced
|  | 4 | Celebrate success | Town Hall membership, Citizen | Social network | Promotional Professional enthousisastic | Show the progress made
3 - Employees equip with eletronic device | Intern | 1 | After the general big presenation on next changes, present this specific change | All employees | Intranet | Professional | explain the holding and the ending of this precise change, be transparent, give all information you can
|  |  | Communication about new tasks, use productivity and collaborative tools to track tasks and help people to maintain their productivity | All employees | Mail, intranet support, meeting | Professional | Why and how we use eletronic device, a new workflow
|  | 2 | Individuals support | employees <=> managers/ referrents | Intranet forum, discussion chats | Conversational | Answer questions, use prepared answed, prepared during global meeting with the communication team
|  | 3 | Increase the skills of all employees | employees | Meeting, Training ritual, Every day, an employee takes 15 to 20 minutes to explain to the other a specific use case | Conversational | Training, learn practices use cases
|  | 4 | Celebrate all success | All employees | Intranet, social networks | Conversational | Congratulate employees, show the progress made to the whole company
| Extern | 1, 2, 3 | Public announcement of the avancement of the implementation | Town Hall membership, Citizen | Social networks | Promotional Professional enthousiastic | Explain the advanced
|  | 4 | Celebrate success | Town Hall membership, Citizen | Social networks | Promotional Professional enthousisastic | Show the progress made
4 - Deploy drones to monitor the street cleenliness | Intern | 1 | After the general big presenation on next changes, present this specific change | All employees | Intranet | Professional | explain the holding and the ending of this precise change, be transparent, give all information you can
|  |  | Communication about new tasks, use productivity and collaborative tools to track tasks and help people to maintain their productivity | Team manager, drone pilot, | Mail, intranet support, meeting | Professional | Why and how we use drones, explain new workflow
|  | 2 | Individuals support | employees <=> managers/ referrents | Intranet forum, discussion chats | Conversational | Answer questions, use prepared answed, prepared during global meeting with the communication team
|  | 3 | Increase the skills of all employees | drone pilots, team manager | Meeting, Training ritual, Every day, an employee takes 15 to 20 minutes to explain to the other a specific use case | Conversational | Training, learn practices use cases
|  | 4 | Celebrate all success | drone pilots, team manager | Intranet, social networks | Conversational | Congratulate employees, show the progress made to the whole company
| Extern | 1, 2, 3 | Public announcement of the avancement of the implementation | Town Hall membership, Citizen | Social networks | Promotional Professional enthousiastic | Explain the advanced, explain wher the citizens can ask questions
|  | 4 | Celebrate success | Town Hall membership, Citizen | Social networks | Promotional Professional enthousisastic | Show the progress made
5 - Change citizen's trashes | Intern | 1 | After the general big presenation on next changes, present this specific change | All employees | Intranet | Professional | explain the holding and the ending of this precise change, be transparent, give all information you can
|  |  | Communication about new tasks, use productivity and collaborative tools to track tasks and help people to maintain their productivity | trucks driver, team manager, maintenance department | Mail, intranet support, meeting | Professional | Why and how we use the new trashes, a new workflow
|  | 2 | Individuals support | employees <=> managers/ referrents | Intranet forum, discussion chats | Conversational | Answer questions, use prepared answed, prepared during global meeting with the communication team
|  | 3 | Increase the skills of all employees | trucks driver, team manager, maintenance department | Meeting, Training ritual, Every day, an employee takes 15 to 20 minutes to explain to the other a specific use case | Conversational | Training, learn practices use cases
|  | 4 | Celebrate all success | trucks driver, team manager, maintenance department | Intranet, social networks | Conversational | Congratulate employees, show the progress made to the whole company
| Extern | 1 | Public announcement of the start of the implementation | Citizens | Personnal letter, Town hall website | Professional | When we'll change trashes, what's the goals, where the citizens can ask questions
|  | 1, 2, 3 | Public announcement of the avancement of the implementation | Town Hall membership, Citizen | Social networks | Promotional Professional enthousiastic | Explain the advanced
|  | 4 | Celebrate success | Town Hall membership, Citizen | Social networks | Promotional Professional enthousisastic | Show the progress made
6 - public application for reporting incident and ask sanitation service | Intern | 1 | After the general big presenation on next changes, present this specific change | All employees | Intranet | Professional | explain the holding and the ending of this precise change, be transparent, give all information you can
|  |  | Communication about new tasks, use productivity and collaborative tools to track tasks and help people to maintain their productivity | Hotline, IT department, team managers | Mail, intranet support, meeting | Professional | Why and how we use this public application, a new workflow
|  | 2 | Individuals support | employees <=> managers/ referrents | Intranet forum, discussion chats | Conversational | Answer questions, use prepared answed, prepared during global meeting with the communication team
|  | 3 | Increase the skills of all employees | Hotline, IT department, team managers | Meeting, Training ritual, Every day, an employee takes 15 to 20 minutes to explain to the other a specific use case | Conversational | Training, learn practices use cases
|  | 4 | Celebrate all success | Hotline, IT department, team managers | Intranet, social networks | Conversational | Congratulate employees, show the progress made to the whole company
| Extern | 1 | Public announcement of the start of the implementation | Citizens | Personnal letter, Town hall website | Professional | When we'll publish this app, what's the goals, where the citizens can ask questions, how to use it
|  | 1, 2, 3 | Public announcement of the avancement of the implementation | Town Hall membership, Citizen | Social networks | Promotional Professional enthousiastic | Explain the advanced
|  | 4 | Celebrate success | Town Hall membership, Citizen | Social networks | Promotional Professional enthousisastic | Show the progress made
7 - Monthle reporting | Intern | 1 | After the general big presenation on next changes, present this specific change | All employees | Intranet | Professional | explain the holding and the ending of this precise change, be transparent, give all information you can
|  |  | Communication about new tasks, use productivity and collaborative tools to track tasks and help people to maintain their productivity | HR department, It department, employees | Mail, intranet support, meeting | Professional | Why and how we use the monthly repport, a new workflow
|  | 2 | Individuals support | employees <=> managers/ referrents | Intranet forum, discussion chats | Conversational | Answer questions, use prepared answed, prepared during global meeting with the communication team
|  | 3 | Increase the skills of all employees | IT department, team managers, HR department | Meeting, Training ritual, Every day, an employee takes 15 to 20 minutes to explain to the other a specific use case | Conversational | Training, learn practices use cases
|  | 4 | Celebrate all success | IT department, team managers, HR department | Intranet, social networks | Conversational | Congratulate employees, show the progress made to the whole company
| Extern | 4 | Public announcement of good results | City Town Hall, Citizens | Social networks | Professional | When we'll publish this app, what's the goals, where the citizens can ask questions, how to use it