## Implementation plans
Implementation plans
Changement concerned | Implementation steps | Employees concerned | Duration
1 - use of the time manager application | Discution with service provider | Head of organization | 4h
| Validation of the specifications | IT department / Head of organization | 4h
| Putting the solutin online | IT department referent | 1w
| Adjustments | IT departent referent | 1w
2 - Trucks with GPS | Hire project manager | HR/ Head of organization | 1w
| External expert | Head of organization / project manager | 2h
| Discution with service provider | Head of organization/Maintenance & IT referents / project manager | 4h
| Validation of the specifications | Maintenance and IT referents / project manager | 4h
| Hardware reception | IT referents / Project Manager | 1d
| GPS configuration | IT department | 1d
| GPS installation | Maintenance department | 2d
| Software configration, data visualisation | IT department/ referent | 1d
| Adjustments | Maintenance/IT department / Project manager | 1w
3 - Employees equip with eletronic device | Hire 2 IT Technicians | HR/ IT Department | 1w
| Discution with employees, specifics needs | IT department referent / Project manager | 1w
| Order to supplier | IT department referent / Project manager | 2h
| device reception, enter in the IT Park manager | IT Department | delivery time + 1w
| Global centralized configuration | IT Department | 2d
| Equipement distribution, all equipment are allocated to one emplyee | IT Department | 1d
4 - Deploy drones to monitor the street cleenliness | Discution with municipality, ask authorization | Head of organization / project manager | 1w
| Order to supplier | project manager | delivery time
| device reception, enter in the Maintenance vehicles Park manager | Maintenance Departmenet | 1d
| Pilothouse installation | Service provider | 2d
| Hire 2 pilots | HR department | 1w
5 - Change citizen's trashes | Discution with the municipality and a service provider | Head of organization / project manager | 4h
| Sensor test in workhouse | Maintenance Departmenet | 4h
| deployment of alert tool to get data from sensor | Service provider/it department | 2d
| Deployment of the new trashes, th eold ones are sold by weight for recycling, and keep some undamager, just in case | Service provider | 1.5m, every start week, change a district trashes, and keep the rest of the weep to monitor and check malfunction
6 - public application for reporting incident and ask sanitation service | Discution with service provider | Head of organization / project manager | 4h
| Validation of the specifications | It departent referent / project manager | 4h
| Putting the solutin online | Srevice provider | 1w
| Adjustments | It departent referent / project manager | 1w
7 - Monthle reporting | Get data and analyze | Chief departmenet | 4d
| take decision, to keep employees motivated and at the right level | Chief department | 4h