## Training plans
Training plans
Changement concerned | Employees concerned | Purpose of training | duration | number of participant concerned
1 - use of the time manager application | HR department | Get data from the application, how to find and read infomrations. | 2h | All the HR department
| HR referent | Get advance data. Specific requests | 1d | The HR referent for the time manger app
| Planning manager | Get working time from team, and create previsional calendar/planning | 2h | All planer department
| Planning manager referent | Advance planning configuration | 1d | The planer referent for the time manager app
| IT department | First level maintenance | 1d | All IT department
| IT referent | Global architecture anderstanding, advanced frequent failure resolution | 2d | The IT egenieer referent for the time manager app
| All employees | Introduction to the tool, basic operations, what it is for, customizable settings | 1h | All employees
2 - Trucks with GPS | Team managers | get truck location, how to identify a truck | 1h | All team manager department
| Team manager referent | advance gps settings, | 2h | Team manager referent 1
| Truck's driver | Check gps on, how to turn on off, how to repport a malfunction to the maintenance team | 1h | All truck's driver
| Mainteance department | How to install a gps on truck | 1h | All maintenance department
| IT department | Check truck's location | 1h | All It department
3 - Employees equip with eletronic device | All employees | Basic presentation | 1h | All employees
| IT new recrue | Basic entreprise onboarding | 2h | IT new recrue
|  | How execute preventive and currative maintenance plan | 3d | IT new recrue
|  | Technical assistance posture | 1d | IT new recrue
4 - Deploy drones to monitor the street cleenliness | Drone pilot | Basic entreprise onboarding | 2h | 2 pilots
| pilots + team manager | how to define a good flight plan | 1d | 2 pilots and 1 team manager
| pilots + team manager | report anomaly procedure | 1h | 2 pilots and 1 team manager
| maintenance Department | Resolve basic failure on drones | 1d | all maintenance department
| maintenance Department Referent | Definition of a maintenance procedure with supplier / after sales service for serious breakdowns | 4h | Maintenance departmenet referent
5 - Change citizen's trashes | Team managers | Get information from trashes sensors | 1h | Team manager
|  | Adapte garbage collector's route | 2h | Team manager
| truck's driver | Get notification of changing route | 1h | All truck's driver